## Estimate
Name | Gifts App
Tech stack | React & Express.js. (Node.js)
Price per Hour | 35 |  |  |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Publication
[5 empty] | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8
Frontend Development (React) | Description | Hours | Duration (days) | Cost | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16
User Registration & Login | Implement user registration for Gifters and Recipients, optional account creation, and secure login using Firebase or another backend authentication method. | 50 | 7 | 1750 | bar: w1 to w2
Asset Catalog & Pricing | Display a catalog of stocks and crypto assets with real-time or periodically updated prices from the market data feed (via API integration). | 70 | 9 | 2450 | bar: w2 to w3
Shopping Cart & Checkout | Develop the shopping cart to allow adding assets, viewing a summary of selected items, and a checkout page with payment gateway integration (Stripe, PayPal, etc.). | 70 | 9 | 2450 | bar: w4 to w5
Gift Certificate Generation | Generate a digital gift certificate, either as a downloadable PDF or via email, containing the breakdown of purchased assets, the total gift value, and the unique order number. | 45 | 6 | 1575 | bar: w6
Order Lookup & Value Display (Recipient) | Implement a page where recipients can enter the Order Number to view the current value of their gift, showing a detailed breakdown of each asset's market value. | 50 | 7 | 1750 | bar: w7 to w8
Redemption Process | Develop the redemption process, allowing recipients to request a cash-out. Include user verification (email, unique order number) and a confirmation before initiating the redemption. | 80 | 10 | 2800 | bar: w8 to w9
Role-Based Access (Frontend) | Implement role-based access controls for different users, ensuring that Gifters, Recipients, and Admins have appropriate access to various parts of the platform | 80 | 10 | 2800 | bar: w10 to w11
UI/UX Design and Frontend Testing | Design a responsive, user-friendly UI using React Material or Cupertino widgets, followed by testing and debugging to ensure smooth performance across desktop and mobile platforms. | 40 | 5 | 1400 | bar: w12
Backend Development (Express.js)
User Management & Authentication | Develop a secure backend for user registration, login, and role management. Integrate authentication services, such as JWT or OAuth. | 45 | 6 | 1575 | bar: w13
Asset Catalog & Pricing | Implement APIs to manage and update asset catalog, pulling data from external market data feeds (stock and crypto APIs) | 50 | 7 | 1750 | bar: w14
Payment Gateway Integration | Integrate payment gateways (Stripe, PayPal) to process user transactions securely during checkout | 60 | 8 | 2100 | bar: w15
Brokerage API Integration | Integrate APIs with brokerage services to handle fractional asset purchases (e.g., Robinhood API, Interactive Brokers API) | 80 | 10 | 2800 | bar: w16
Gift Certificate Generation & Management | Backend logic to create and manage digital gift certificates, linking them to orders and assets | 50 | 7 | 1750
Redemption & Payout System | Develop logic for processing redemption requests, verifying the user's identity, liquidating assets, and processing payouts to recipients | 80 | 10 | 2800
Admin & Moderator Panel | Build backend systems for Admins and Moderators to manage assets, transactions, user support, and financial configurations. | 70 | 9 | 2450
Total |  | 870 | 113 | 30450